## Sheet1
|  | Dev | QA | Product Mktg | Tech Pubs | CS | Ops/ Finance | SE/ Sales | PM | Exec
Phase 1 Requirements | MRD/PRD (Preliminary) |  |  | X
| Prioritized ECR's/Bugs |  |  |  |  | X |  | X
| Feature/Limits Sizing | X | X
| Resource Estimate | X | X
| Target Schedule | X | X
| Business Justification |  |  | X
| MRD/PRD (Final) | X | X | X |  | X |  | X
| REQUIREMENTS REVIEW | X | X | X | X | X | X | X | X | X
Phase 2 Planning | Functional Spec for each Feature | X
| Scoped Schedule | X | X
| Development Plan | X
| Upgrade Process Defined | X | X |  |  | X |  | X
| Test Plan |  | X
| Manufacturing Plan | [5 empty] | X
| Build Plan | [7 empty] | X
| Resource Requirements | X | X | X | X | X | X | X
| Detailed Schedule | X | X | X | X | X | X | X
| Beta Site Planning |  |  | X |  | X |  | X
| Integrated Schedule | [7 empty] | X
| Business Case / Cost Analysis |  |  | X |  |  | X
| MRD/PRD (Committed) | X | X | X |  | X |  | X
| PLANNING REVIEW | X | X | X | X | X | X | X | X | X
Phase 3 Development, Integration & Quality Assurance | Feature Development/Unit Tests | X | [8 empty] | FCS Review (Phase 3 Exit) Goals
| Test Cases |  | X | [7 empty] | –Specify what features, code improvements, limits testing, and defect fixes were included in the project
| Weekly Submittals/Notes | X | [8 empty] | –Share status of Phase 3 deliverables
| Defect Triage | X | X |  |  | X |  |  |  |  | –Demonstrate shipment readiness
| Unit Tests | X | [8 empty] | –Obtain management approval from those outside the project core team
| Functional Tests |  | X
| System Tests |  | X
| Weekly Status | X | X | [5 empty] | X
| Code Complete | X
| Soak Testing |  | X
| Lock Release Branch | X | X
| Mightydog Testing | [5 empty] | X
| External Beta Testing |  |  |  |  | X
| Documentation Reviewed | X | X | X | X | X |  | X
| All MF Bugs Closed | X | X
| No OPEN QA Defects |  | X
| Documentation Released |  |  |  | X
| Gold Master |  | X |  |  |  | X
| Wrap Up Report |  | X
| FCS REVIEW | X | X | X | X | X | X | X | X | X
Phase 4 Post-FCS | TOI | X | X |  |  | X |  |  | X
| Continued Soak Tests |  | X
| GA Release |  |  |  |  | X | X | X
| ASSIST Site Updated |  |  |  |  | X
| Notify Customers/Partners |  |  |  |  | X
| Open Sustaining Branch | X
| Post Mortem Review | X | X | X | X | X | X | X | X
| Product Maintenance & Support |  |  |  |  | X
| Escalation Resolution | X | X |  |  | X
| EOL REVIEW | X | X | X | X | X | X | X | X | X
Phase 5 EOL | Notify Customers |  |  |  |  | X |  | X
| End Support |  |  |  |  | X