## Sheet1
Task	Work Weeks
	Linux	NetBSD	OpenBSD 2.8
Create toolchain	done	1	0
Create build infrastructure and makefiles	1	1	1
Develop porting framework for developers	1	0	0
OS bring up on Cougar	4	4.5	3
Assemble filesystem	done	0.5	0
Assemble kernel bits	1	1	0
boot kernel on Bobcat TXRX processor	2	2	2
boot kernel on Cougar hardware	1	1	1
Port EverON to Cougar	29	9	13
Startup scripts	1	1	0.5
root filesystem packaging	3	3	0.5
upgrade utility	2	2	0
management driver	1	1	1
chassis driver	1	1	1
GPP <--> TXRX TCP port forwarding virtual networking	1	1	0
Port GPP applications code	20	0	10
OS bring up on Bobcat	4	5	0
kernel config	0.5	0.5	0
extra drivers, if any	0	1	0
boot kernel on PMC processor	0.5	0.5	0
GPP <--> TXRX TCP port forwarding virtual networking	1	1	0
management driver	1	1	0
chassis driver	1	1	0

Total:	35	15.5	17